## Problem
Activity | Option | Duration | amt of equipment deeded per day | total cost | Basic Cost per day | 100
A | 1 | 0 | 0 | 0
B | 1 | 2 | 1 | 135
| 2 | 3 | 0 | 65
C | 1 | 1 | 1 | 160
| 2 | 3 | 0 | 90
D | 1 | 3 | 1 | 170
| 2 | 4 | 0 | 100
E | 1 | 5 | 1 | 155
| 2 | 7 | 0 | 85
F | 1 | 4 | 1 | 150
| 2 | 6 | 0 | 80
G | 1 | 1 | 1 | 190
| 2 | 4 | 0 | 120
H | 1 | 0 |  | 0
Maximum amount of equipment available per day |  |  | 1
0

## Reduced problem
# | Activity Name | Option | Duration (Ci) | amt of equipment deeded per day | [7 empty] | Matrix Form
1 | A | 1 | 0 | 0 |  |  |  |  | # (i) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | values at end of minimization |  | RHS
2 | B | 1 | 2 | 1 |  |  |  |  | Activity Name | B | C | D | E | F | G | H
3 | C | 1 | 1 | 1
4 | D | 1 | 3 | 1 |  |  |  |  | Vi (Decision variable)
5 | E | 1 | 5 | 1 | [15 empty] | 0
6 | F | 1 | 4 | 1 |  |  |  |  | Obj.Function (minimize) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
7 | G | 1 | 1 | 1
8 | H | 1 | 0 | [17 empty] | Interprettion
[9 empty] | Temporal constraints | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | >= | 2 |  | E-B>=2 | V4-V1>=2
| Maximum amount of equipment available per day |  |  | 1 | [5 empty] | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | >= | 2
[10 empty] | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | >= | 1
[10 empty] | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | >= | 4
[10 empty] | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | >= | 1
[10 empty] | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | >= | 5
[10 empty] | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | >= | 3
Resource Constraints for activity B | bar: 1 to Matrix Form 5
[5 empty] | di | di-v | di-(v+c) | less-than constraint | t1(di) | greater-than constraint | less-than constraint | t2(di) | greater-than constraint |  | t(di)
[5 empty] | 1 | 1 | -1 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 2 | 2 | 0 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 3 | 3 | 1 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 4 | 4 | 2 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 5 | 5 | 3 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 6 | 6 | 4 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 7 | 7 | 5 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 8 | 8 | 6 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 9 | 9 | 7 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 10 | 10 | 8 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 11 | 11 | 9 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 12 | 12 | 10 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 13 | 13 | 11 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 14 | 14 | 12 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 15 | 15 | 13 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 16 | 16 | 14 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 17 | 17 | 15 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
[5 empty] | 18 | 18 | 16 | 0 |  | 1: -1000; 2: 0; Matrix Form 4: -1000; Matrix Form 6: 0
The step function for each activity can be modelled as the difference of these two functions:
t1(di) =1 if di>v else t1(di)=0 : M*t1(di)≥di-v≥−M*(1−t1(di))
t2(di) =1 if d>v+c else t2(di)=0 : M*t2(di)≥di-(v+c)≥−M*(1−t2(di))

## Matrix
| A | B | C | D | values at end of minimization
min. | 0 | 0 | 0 | 1 | 4
const. | 1 | -1 | 0 | 0 | -2 | <= | -1
| 1 | 0 | -1 | 0 | -1 | <= | -1
| 0 | 1 | 0 | -1 | -2 | <= | -2
| 0 | 0 | 1 | -1 | -3 | <= | -3
Variables | 0 | 2 | 1 | 4